## Timeline
Spring 2024:
Category | Task | Subtask | Target Date | Status | January | February | March | April
1: Expand E. coli FAS Model | 1A: Run model and recreate plots |  |  | Done
| 1B: Recreate FabF C8 mutant results | I108F mutant - figure out what Katie changed to make ME2 Figure S5 | 2024-01-22 | Done
| 1C: Add P. putida FabG | Figure out what needs to be reparametrized and what is from experimental data | 2024-02-05 | Done
|  | Find what changes need to be done to alter the model from EC FabG to PP FabG | 2024-02-05 | Done
|  | Add changes to the model and compare against 2D and 2E from the manuscript | 2024-03-11 | Done
|  | Figure out differences between model and experiment | 2024-04-29 | In Progress
| 1D: Add ACC | Find kinetic reactions and add diff eqs to the model | 2024-02-12 | Done
|  | Find data in literature for kinetic parameters/estimates | 2024-04-29 | In Progress
|  | Decide what optimizations parameters to include/add | 2024-04-29 | In Progress
|  | Reoptimize and run the model | 2024-04-29 | In Progress
|  | Keep track of steps taken/make a cheatsheet for how to add an enzyme | 2024-04-29 | In Progress
| 1E: Make the model run faster (fun bonus task) | Find redundancies and functions that take the most time (vectorize nested loops) |  | On going
|  | Try new methods to speed things up (Alpine, Bertha, etc.) |  | On going
2: Expand model to pennycress FAS | 2A: Create pennycress FAS diagram | Make side-by-side diagram with E. coli FAS | 2024-03-11 | Not Started
| 2B: Reduce the FAS (37 to ?) | Figure out main enzymes to be included (redundancy? Expressed in developing seeds?) | 2024-03-25 | Not Started
|  | Find kinetic equations, parameters, and decide what might need to be Michaelis-Menten | 2024-04-08 | Not Started
| 2C: Validation data | What data will be needed to fit the model? | 2024-04-08 | Not Started
| 2D: Make new model | Add all equations and parameters | 2024-04-22 | Not Started
|  | Decide where to add optimization scaling factors | 2024-04-22 | Not Started
| 2E: Validate with data | Optimize to fit data, troubleshoot | TBD | Not Started
| 2F: Sensitivity analysis | Find what steps are most important for objectives | TBD | Not Started
3: MD | 3A: Software download tutorials |  | 2024-01-08 | Done
| 3B: Read papers (Anika) |  |  | In Progress
| 3C: Work with Anika on current project | MD tutorials done, next steps: learn simultations, learn analysis |  | In Progress
| 3D: New Project |  |  | Not Started
Summer 2024:
Category | Task | Subtask | Target Date | Status | May | June | July |  | August
1: Expand E. coli FAS Model | 1A: P. putida FabG |  |  | Not Started
Not Started
Not Started
| 1B: ACC |  | 2024-05-20 | Not Started
Not Started
Not Started
| 1C: Optimize code |  |  | Not Started
Not Started
Not Started
2: KS Mutants | 2A: Run simulations |  |  | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
3: B5 Modeling Effort | 3A: Model of Pennycress FAS |  |  | Not Started
Not Started
Not Started
| 3B: Analysis of interesting phenomena | Product profile email thread - acyl-ACP concentrations same but product profiles different |  | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started